REDDITFLOW

AI Visibility & Community Engagement Platform

Complete Product Blueprint & Implementation Guide

From MVP to Premium SaaS Product

Prepared for: Saksham Mittal | YordIndia

March 2026

# 1. Executive Summary

RedditFlow is a partially-built SaaS platform for discovering Reddit opportunities and drafting AI-powered replies for brands. After a comprehensive audit of every backend module, frontend page, database model, API endpoint, and user flow, this document provides a complete blueprint to transform it from an incomplete MVP into a premium AI Visibility and Community Engagement platform that surpasses CrowdReply.

Current State Assessment

| Dimension | Score | Verdict |
| --- | --- | --- |
| Backend Architecture | 5/10 | Solid patterns, critical operational gaps |
| Frontend / UI Quality | 4/10 | Functional MVP, needs complete UX overhaul |
| Feature Completeness | 3/10 | Reddit-only, missing AI visibility core |
| Production Readiness | 2/10 | Not safe for public/paid launch |
| UX / Onboarding | 3/10 | Confusing flows, no guidance, poor feedback |
| Security Posture | 3/10 | Auth works, everything else needs hardening |
| Scalability | 2/10 | Will fail beyond 100 concurrent users |

What Must Change

The platform needs transformation across five dimensions to become a product customers will pay for and trust:

- Core Product Gap: The entire AI Visibility Tracking engine (prompt monitoring, model runners, citation extraction, share of voice) does not exist yet. This is the product CrowdReply customers actually pay for.

- Platform Coverage: Reddit-only is too narrow. Quora and Facebook monitoring are table-stakes for V1 parity.

- UX Overhaul: Every page needs loading states, error handling, form validation, and guided onboarding. The current experience will frustrate users within minutes.

- Backend Hardening: No logging, no rate limiting, no async scan processing, synchronous API calls that block the server, silent exception swallowing, and no monitoring. Production deployment at current state would be irresponsible.

- Growth Infrastructure: No email system, no password reset, no notification center, no activity feeds, no team collaboration, no reporting exports. These are expected features in any modern SaaS.

# 2. Full Gap Analysis

## 2.1 Product Gaps

A. AI Visibility Tracking (Entirely Missing)

This is the single biggest gap. CrowdReply's core value proposition is monitoring how brands appear in AI model responses. Your platform has zero functionality here.

| Missing Feature | Priority | Description |
| --- | --- | --- |
| Prompt Library & Management | Critical | Define and organize prompts by intent, persona, funnel stage, geography. This is the foundation of the entire AI tracking product. |
| AI Model Runner Service | Critical | Execute prompts across ChatGPT, Perplexity, Gemini, Claude via their APIs. Store full responses with timestamps. |
| Brand Mention Detection | Critical | NLP extraction of brand and competitor names from AI responses. Must handle variations, abbreviations, and context. |
| Citation URL Extraction | Critical | Parse AI responses to identify all cited/linked sources. Normalize URLs, deduplicate domains. |
| Share of Voice Calculation | Critical | Calculate percentage of prompts where brand appears vs competitors. Track over time per model. |
| Historical Trend Storage | High | Time-series data for all visibility metrics. Needs columnar storage (ClickHouse/TimescaleDB). |
| Anomaly Detection & Alerts | High | Detect sudden drops or spikes in brand visibility. Alert via Slack/email. |
| Multi-Model Comparison | High | Side-by-side view showing how brand appears differently across AI models. |

B. Citation & Source Intelligence (Entirely Missing)

| Missing Feature | Priority | Description |
| --- | --- | --- |
| Citation Source Mapping | Critical | For each AI response, extract and store which URLs/domains are cited. |
| Source Gap Analysis | Critical | Show where competitors are cited by AI but your brand is not. |
| Domain Influence Graph | High | Map which domains appear most often across prompt categories. |
| URL-Level Influence Scoring | High | Score individual URLs by citation frequency, recency, model coverage. |
| Content Format Classification | Medium | Classify cited content type: review, comparison, tutorial, discussion, listicle. |
| Source Freshness Weighting | Medium | Track how recently cited sources were published/updated. |

C. Platform Coverage Gaps

| Missing Feature | Priority | Description |
| --- | --- | --- |
| Quora Monitoring | Critical | Second community platform. Quora answers heavily influence Perplexity. |
| Facebook Group Monitoring | High | Third platform. Important for B2C brands. |
| Google AI Overviews Tracking | High | Google's AI answers are the highest-traffic AI surface. |
| Microsoft Copilot Tracking | Medium | Growing enterprise AI surface. |
| Cross-Platform Unified Feed | High | Single view for opportunities from all platforms. |

## 2.2 UX Gaps

Critical UX Failures

| UX Gap | Severity | Impact |
| --- | --- | --- |
| No Loading States | Critical | Generate keywords, run scan, analyze website: zero visual feedback. Users click multiple times. |
| Silent API Failures | Critical | Generic 'Could not create' messages. No distinction between network/validation/server errors. |
| Missing Empty States | High | Pages show nothing when data absent. No guidance on what to do first. |
| No Form Validation | High | No client-side validation. URL format, email format, required fields: none checked before submit. |
| No Confirmation Dialogs | High | Delete keyword, persona, subreddit: instant deletion, no 'Are you sure?' prompt. |
| Broken Sequential Workflow | High | Discovery page has 4 cards in grid. Should be step 1, 2, 3 with enforced order. |
| Incomplete Persona Form | High | Model supports pain_points, goals, triggers, preferred_subreddits. Form only captures name, role, summary. |
| No Password Reset | Critical | User forgets password: completely locked out. No recovery flow exists. |
| No Edit Capability | High | Created a persona with a typo? Can't edit it. Must delete and recreate. |
| Reply Draft in Warning Box | Medium | AI-generated replies display in a dashed warning-styled '.notice' div instead of a proper content card. |

## 2.3 UI Gaps

| UI Gap | Severity | Impact |
| --- | --- | --- |
| No Design System | High | Ad-hoc CSS classes. No shared component library. 16 different gap sizes. |
| '.notice' Overloaded | High | Same styling for warnings, errors, info, and success. Users cannot distinguish states. |
| No Responsive Mobile Nav | High | Sidebar collapses poorly. No hamburger menu. Touch targets too small. |
| Weak Typography Hierarchy | Medium | Mixed serif/sans-serif. Some text at 12px, unreadable on some screens. |
| No Skeleton Loading | Medium | Pages appear blank while loading, then pop in. Jarring experience. |
| Color-Only State Indicators | Medium | Green badge for 'done' has no icon or text fallback. Inaccessible to colorblind users. |
| No Toast Notification System | High | Success/error feedback appears in inline divs that are easy to miss. |

## 2.4 Backend / Technical Gaps

| Technical Gap | Severity | Description |
| --- | --- | --- |
| No Structured Logging | Critical | Zero logging. Production failures completely invisible. |
| Synchronous Scan in HTTP Handler | Critical | Reddit API calls block the web server. One slow scan blocks all users. |
| Silent Exception Swallowing | Critical | 'except Exception: continue' in scan loop. Errors vanish. |
| No Rate Limiting | Critical | Any endpoint can be hammered. No per-user throttling. |
| CORS Allows All Methods/Headers | High | Wide-open CORS configuration. Security risk. |
| No SSRF Protection | High | Website analysis fetches any URL. Could access internal services. |
| No Token Revocation | High | JWT tokens valid 24h with no blacklist. Compromised tokens cannot be revoked. |
| No Request Tracing | High | No correlation IDs. Cannot trace requests across services. |
| N+1 Query Patterns | High | Dashboard loads all projects then queries separately. Will timeout at scale. |
| No Pagination | High | List endpoints return all records. 1000+ opportunities loaded into memory. |
| No Database Migrations | High | No Alembic. Schema changes are manual and error-prone. |
| No Email Service | High | Invitations created but never sent. SMTP configured but no send function. |
| No Soft Deletes | Medium | Hard deletes everywhere. Accidentally deleted data is permanently lost. |
| No Health Check Endpoints | Medium | Cannot monitor Reddit API, OpenAI, or database connectivity. |
| Scoring Algorithm is Static | Medium | Hardcoded weights. No learning from user feedback. |
| No Webhook Delivery Tracking | Medium | Webhooks fire-and-forget. No retry, no delivery logs. |
| No Usage Metrics Table | Medium | Entitlement limits checked at call time with race conditions. |
| Redemption Codes Never Expire | Low | No expires_at field. Codes reusable indefinitely. |

## 2.5 Business / Growth Gaps

| Growth Gap | Severity | Description |
| --- | --- | --- |
| No Social Proof | High | No testimonials, case studies, user count, or trust badges on marketing page. |
| No Onboarding Email Sequence | High | User signs up and gets nothing. No welcome email, no tips, no activation nudge. |
| No In-App Upgrade Prompts | High | Hitting plan limits shows a generic error. Should show upgrade CTA with comparison. |
| No Usage Dashboard | Medium | Users cannot see how much of their plan limits they have consumed. |
| No Referral System | Medium | No viral loop. No way for users to invite others with incentive. |
| No Changelog / What's New | Low | Users don't know about new features or improvements. |
| No Help Center | Medium | No documentation, FAQ, or support contact beyond the UI itself. |
| Missing Trust Signals | High | No security badges, SOC2 mention, data handling policy, or uptime guarantee. |

# 3. Priority-Based Improvement Plan

Every gap classified into three tiers. Critical items block launch. Important items block growth. Nice-to-have items are competitive differentiators.

## 3.1 Critical (Must Fix Before Any Public Launch)

| Item | Area | Estimate |
| --- | --- | --- |
| Add structured logging + Sentry error tracking | Backend | 2-3 days |
| Move scan operations to Celery async tasks | Backend | 3-4 days |
| Add rate limiting middleware (SlowAPI) | Backend | 1-2 days |
| Fix CORS to whitelist specific methods | Backend | 1 hour |
| Add SSRF protection on URL fetching | Backend | 1 day |
| Build password reset flow (backend + frontend) | Full Stack | 2-3 days |
| Add loading spinners to all async operations | Frontend | 2-3 days |
| Build toast notification system (success/error/warning/info) | Frontend | 2-3 days |
| Add client-side form validation on all forms | Frontend | 2-3 days |
| Build Prompt Library and Management UI | Full Stack | 5-7 days |
| Build AI Model Runner Service (ChatGPT + Perplexity) | Backend | 7-10 days |
| Build brand mention detection in AI responses | Backend | 3-5 days |
| Build citation URL extraction | Backend | 3-5 days |
| Build email service for invitations and notifications | Backend | 2-3 days |
| Add pagination to all list endpoints | Backend | 2-3 days |

## 3.2 Important (Must Build for Growth)

| Item | Area | Estimate |
| --- | --- | --- |
| Quora monitoring integration | Backend | 5-7 days |
| Share of voice dashboard | Full Stack | 5-7 days |
| Source gap analysis view | Full Stack | 4-5 days |
| Complete persona form (all fields) | Frontend | 2-3 days |
| Add edit/delete for all entities | Full Stack | 3-4 days |
| Build guided onboarding wizard | Frontend | 3-5 days |
| Add confirmation dialogs for destructive actions | Frontend | 1-2 days |
| Fix Discovery page into clear sequential steps | Frontend | 2-3 days |
| Build Notification Center | Full Stack | 3-5 days |
| Add token revocation and refresh token flow | Backend | 2-3 days |
| Set up Alembic database migrations | Backend | 1-2 days |
| Build usage dashboard (plan consumption) | Full Stack | 2-3 days |
| Add in-app upgrade prompts at limit boundaries | Frontend | 1-2 days |
| Google AI Overviews tracking | Backend | 5-7 days |
| Competitor comparison dashboard | Full Stack | 3-5 days |
| Build proper design system and component library | Frontend | 5-7 days |
| Add responsive mobile navigation | Frontend | 2-3 days |

## 3.3 Nice-to-Have (Competitive Differentiators)

| Item | Area | Estimate |
| --- | --- | --- |
| Facebook group monitoring | Backend | 5-7 days |
| Experiment framework (campaign A/B testing) | Full Stack | 10-15 days |
| CRM/GA4/HubSpot attribution connectors | Backend | 7-10 days |
| Revenue attribution engine | Full Stack | 10-15 days |
| Domain influence graph visualization | Frontend | 5-7 days |
| Policy-safe auto-drafting for community responses | Backend | 5-7 days |
| Creator/expert marketplace | Full Stack | 15-20 days |
| Region/persona simulation | Backend | 7-10 days |
| Predictive citation probability model | Backend | 10-15 days |
| Budget allocator across channels | Full Stack | 5-7 days |
| Keyboard shortcuts and power-user features | Frontend | 2-3 days |
| Help center with searchable documentation | Full Stack | 3-5 days |
| Referral system | Full Stack | 3-5 days |

# 4. Complete Feature Architecture

The platform should be organized into seven core modules, each with clear responsibilities and data boundaries.

## 4.1 Module Architecture

| Module | Features | Key Data Models |
| --- | --- | --- |
| Visibility Intelligence | Prompt library, AI model runners, brand mention detection, share of voice, trend analysis, anomaly alerts | PromptSet, PromptRun, AIResponse, BrandMention, VisibilitySnapshot |
| Source Intelligence | Citation extraction, source mapping, domain influence graph, source gap analysis, freshness scoring | Citation, SourceDomain, InfluenceScore, SourceGap |
| Social Listening | Reddit monitoring, Quora monitoring, Facebook monitoring, opportunity scoring, early thread detection, unified feed | Opportunity, ScanRun, MonitoredSubreddit, MonitoredQuoraTopic, MonitoredFBGroup |
| Safe Activation | AI reply drafting, original post drafting, compliance scoring, approval workflows, posting queue, employee advocacy | ReplyDraft, PostDraft, ComplianceCheck, ApprovalRequest, PostingTask |
| Experimentation | Campaign setup, A/B testing, intervention logging, outcome measurement, statistical analysis | Campaign, Experiment, Intervention, OutcomeMeasurement |
| Attribution | CRM connectors, analytics integration, revenue attribution, executive reporting, funnel tracking | AttributionEvent, FunnelStage, RevenueImpact, IntegrationSync |
| Platform Core | Auth, workspaces, projects, billing, notifications, audit, settings, team management | AccountUser, Workspace, Membership, Project, Subscription, Notification, AuditEvent |

## 4.2 New Database Models Required

The following models must be added to support the complete feature set. Each includes the essential fields and relationships.

Visibility Intelligence Models

| Model | Fields | Purpose |
| --- | --- | --- |
| PromptSet | id, project_id, name, category (intent/persona/funnel), prompts (JSON array), is_active, created_at | Groups related prompts for batch execution |
| PromptRun | id, prompt_set_id, model_name, prompt_text, status (queued/running/complete/failed), scheduled_at, completed_at | Individual prompt execution record |
| AIResponse | id, prompt_run_id, model_name, raw_response (text), brand_mentioned (bool), competitor_mentions (JSON), sentiment, created_at | Stores full AI response with extracted metadata |
| BrandMention | id, ai_response_id, brand_name, mention_type (direct/indirect/competitor), context_snippet, position_in_response | Individual brand occurrence within a response |
| VisibilitySnapshot | id, project_id, model_name, date, total_prompts, brand_mentioned_count, share_of_voice (float), top_competitors (JSON) | Daily aggregated visibility metrics |

Source Intelligence Models

| Model | Fields | Purpose |
| --- | --- | --- |
| Citation | id, ai_response_id, url, domain, title, content_type (review/comparison/discussion/tutorial), first_seen_at | Individual URL cited in an AI response |
| SourceDomain | id, project_id, domain, total_citations, avg_influence_score, last_cited_at, category | Aggregated domain-level intelligence |
| SourceGap | id, project_id, competitor_name, domain, citation_count, gap_type (competitor_cited_brand_not), discovered_at | Where competitors appear but brand does not |

Platform Enhancement Models

| Model | Fields | Purpose |
| --- | --- | --- |
| Notification | id, workspace_id, user_id, type, title, body, read_at, action_url, created_at | In-app notification center |
| ActivityLog | id, workspace_id, user_id, action, entity_type, entity_id, metadata (JSON), created_at | User activity timeline |
| UsageMetric | id, workspace_id, metric_key, current_value, limit_value, period_start, period_end | Track plan consumption atomically |
| PasswordResetToken | id, user_id, token, expires_at, used_at | Secure password recovery |
| EmailTemplate | id, template_key, subject, html_body, text_body | Transactional email templates |

# 5. Screen-by-Screen Product Structure

Every screen in the platform, organized by navigation structure. Each entry defines what exists, what is missing, and the final improved version.

## 5.1 Navigation Architecture (Redesigned)

The current sidebar has flat navigation with unclear priority. The redesigned navigation groups screens by workflow stage and separates core from advanced features.

| Screen | Route | Purpose | Current State | Category |
| --- | --- | --- | --- | --- |
| Dashboard | /app/dashboard | Home base: KPIs, quick actions, activity feed, setup progress | Exists (basic) | Core |
| AI Visibility | /app/visibility | Prompt tracking, share of voice, model comparison, trends | Missing entirely | Core |
| Source Intelligence | /app/sources | Citations, domain graph, source gaps, content analysis | Missing entirely | Core |
| Opportunities | /app/opportunities | Unified feed from Reddit/Quora/Facebook, scoring, filtering | Partial (Discovery) | Core |
| Content Studio | /app/content | Reply drafts, post drafts, approval queue, posting history | Partial (within Discovery) | Core |
| Brand Setup | /app/brand | Brand profile, website analysis, voice configuration | Exists (needs polish) | Setup |
| Audience | /app/audience | Personas, keywords, monitored communities | Exists (split across pages) | Setup |
| Campaigns | /app/campaigns | Experiment setup, A/B tests, intervention tracking | Missing entirely | Advanced |
| Reports | /app/reports | Executive dashboards, exports, scheduled reports | Missing entirely | Advanced |
| Settings | /app/settings | Workspace, team, billing, integrations, API keys, webhooks | Partial | System |

## 5.2 Dashboard (Redesigned)

Current Problems

- Step checklist exists but does not lock unavailable steps or show progress percentage

- KPI grid shows raw zeroes with no context or links

- Top opportunities section lacks 'View all' link and score explanation

- No activity feed or recent actions

- No upgrade prompts when approaching plan limits

Redesigned Dashboard Layout

The dashboard should be organized in a clear grid with four main zones:

- Zone 1: Setup Progress Bar (top): Horizontal progress bar: 'Step 3 of 5 complete: 60%' with clickable step icons. Only appears until setup is done. Dismissible after completion.

- Zone 2: KPI Cards Row (below progress): Four metric cards: AI Visibility Score (share of voice %), Active Opportunities (count with trend arrow), Engagement Rate (drafts sent / opportunities found), Source Coverage (domains where brand is cited). Each card is clickable and links to the relevant detail page.

- Zone 3: Two-Column Main Area: Left column (60%): Top Opportunities feed with score, platform icon, title, subreddit, and quick-action buttons. Right column (40%): AI Visibility Trend chart showing 7-day share of voice line graph.

- Zone 4: Activity Timeline (bottom): Recent actions: 'You generated a reply for r/SaaS thread', 'Scan completed: 12 new opportunities', 'Brand visibility dropped 5% on Perplexity'. Links to each event.

Required Components

- ProgressBar component with step indicators

- MetricCard component with value, trend, label, link

- OpportunityCard component with platform icon, score badge, title, actions

- MiniChart component for inline sparkline/trend visualization

- ActivityItem component with icon, text, timestamp, link

- EmptyState component with illustration, heading, description, CTA button

## 5.3 AI Visibility Screen (New)

This is the most important new screen. It is the core of the CrowdReply-equivalent product.

Layout Structure

- Header Bar: Title: 'AI Visibility', date range picker, model filter dropdown (All / ChatGPT / Perplexity / Gemini / Claude), refresh button

- KPI Row: Four cards: Share of Voice (%), Prompt Coverage (brand mentioned / total prompts), Citation Count, Competitor Gap Count

- Main Chart: Line chart: Share of voice over time, one line per AI model. Tooltip shows date, percentage, and delta from previous day

- Prompt Results Table: Columns: Prompt text, Model, Brand Mentioned (yes/no icon), Competitors Found, Citations Count, Last Run. Sortable. Filterable by model and mention status

- Competitor Comparison: Horizontal bar chart: brand vs top 5 competitors by share of voice. Toggle between models

Backend Requirements

- GET /v1/visibility/summary: Return aggregated share of voice, prompt coverage, citation count

- GET /v1/visibility/trends: Return time-series data for chart (date, model, share_of_voice)

- GET /v1/visibility/prompts: Return paginated prompt run results with mention/citation data

- GET /v1/visibility/competitors: Return competitor share of voice rankings

- POST /v1/visibility/run: Trigger prompt execution across selected models

## 5.4 Source Intelligence Screen (New)

Layout Structure

- Domain Leaderboard: Table: Domain, Total Citations, Avg Influence Score, Most Cited For (prompt category), Last Cited. Sortable by all columns.

- Source Gaps Panel: Cards showing: 'Competitor X is cited on domain.com for prompt Y, but you are not.' Each card has a CTA: 'Create content for this source'.

- Content Type Breakdown: Pie chart: what types of content get cited most (reviews: 35%, comparisons: 25%, discussions: 20%, tutorials: 15%, other: 5%)

- Citation Timeline: When citations first appeared and how they changed over time. Useful for seeing if recent actions influenced citations.

## 5.5 Opportunities Screen (Redesigned)

Current Problems

- Discovery page mixes keyword management, subreddit discovery, scanning, and opportunity viewing in one page

- No filtering, sorting, or search within opportunities

- Reply drafts display in a warning-styled div

- No platform indicator (everything is Reddit)

Redesigned Layout

- Filter Bar: Platform filter (Reddit/Quora/Facebook), Status filter (New/Saved/Drafting/Posted/Ignored), Score range slider, Date range, Subreddit/Topic filter, Search text input

- Opportunities List: Card per opportunity: Platform icon, Score badge (color-coded: green 70+, yellow 40-69, red under 40), Title, Subreddit/Topic name, Body excerpt (2 lines), Posted time ago, Comment count, Action buttons (Save, Draft Reply, Ignore)

- Opportunity Detail Drawer: Slide-in panel from right: Full post content, Score breakdown (visual: keyword match 35pts, intent 20pts, freshness 15pts), Reply drafts list with versions, Generate new draft button, Edit draft inline, Copy to clipboard, Mark as posted

- Bulk Actions Bar: Select multiple opportunities, bulk ignore, bulk save, bulk generate drafts

## 5.6 Content Studio Screen (New)

Centralizes all content creation, review, and posting in one place. Currently this functionality is scattered.

Tabs

- Drafts: All reply and post drafts with status (draft/in review/approved/posted). Click to edit, preview, submit for approval.

- Approval Queue: Drafts pending team approval. Reviewer can approve, reject with notes, or request changes.

- Posted: History of all posted content with performance metrics (upvotes, replies received) if available.

- Templates: Prompt templates for different content types. Currently the Prompts page, moved here for logical grouping.

## 5.7 Brand Setup Screen (Improved)

Current Problems

- Split into two confusing columns: save form on left, analysis on right

- 'Fill from website' and 'Analyze website' appear as separate features but do the same thing

- Six textarea fields with no guidance, character limits, or examples

- Analysis results display is unclear: editable or read-only?

Redesigned Flow

Convert to a single-column guided setup wizard with three steps:

- Website Analysis: Paste URL, click 'Analyze', see extracted data preview. Accept or modify each field.

- Brand Voice: Set tone (formal/casual slider), CTA style, voice notes with inline examples showing how each setting affects generated content.

- Review and Save: Summary card of all brand settings. Edit any field inline. Save button.

## 5.8 Audience Screen (Consolidated)

Merge current Persona, Discovery keywords, and Subreddits pages into one unified Audience setup screen with tabs.

Tab 1: Personas

- Full persona form with ALL model fields: name, role, summary, pain_points, goals, triggers, preferred_subreddits

- Card-based display showing all persona details

- Edit and delete with confirmation

- AI generate with preview before saving

Tab 2: Keywords

- Keyword list with priority scores and source tags

- Bulk add (comma-separated or paste from spreadsheet)

- AI suggest with preview

- Delete with confirmation

- Usage indicator: '23 of 50 keywords used'

Tab 3: Communities

- Combined list: Reddit subreddits, Quora topics, Facebook groups

- Platform icon for each

- Fit score and activity score with visual bars

- Analysis expandable section

- Add manually or discover with AI

## 5.9 Settings Screen (Restructured)

Current settings page dumps webhooks and API keys with minimal explanation. Restructure into clear tabs.

Tab Structure

| Tab | Contents |
| --- | --- |
| General | Workspace name, slug, timezone, default language, logo upload |
| Team | Member list with roles, invite new members, remove members, role management |
| Billing | Current plan card, usage meters, upgrade/downgrade buttons, payment method, invoice history |
| Integrations | Slack, email, CRM connectors. Each with connect/disconnect toggle and status indicator |
| API & Webhooks | API keys with create/revoke, webhook endpoints with event selection, delivery logs, test button |
| Security | Password change, two-factor authentication toggle, active sessions list, login history |
| Notifications | Email notification preferences: opportunity alerts, weekly digest, visibility drops, team activity |

# 6. Improved User Flows

## 6.1 First-Time User Onboarding

The current experience drops new users into a dashboard with a checklist but no context. The redesigned onboarding guides users through a focused 5-minute setup.

| Step | Experience | API Required |
| --- | --- | --- |
| 1. Welcome Screen | After registration, show: 'Welcome to RedditFlow, [Name]! Let's set up your brand in 5 minutes.' Two paths: 'Quick Setup (paste your website)' or 'Manual Setup'. Most users pick quick setup. | None needed (new page) |
| 2. Website Analysis | User pastes URL. System analyzes in 3-5 seconds with progress animation. Shows extracted: brand name, product summary, target audience, voice. User can accept all or modify individual fields. | POST /v1/brand/{id}/analyze (exists) |
| 3. Persona Generation | System auto-generates 3 personas based on brand. Shows preview cards. User can accept, modify, or skip. Each persona shows name, role, pain points. | POST /v1/personas/generate (exists) |
| 4. Keyword Discovery | System generates 10-15 keywords from brand + personas. Shows in a checklist format. User toggles which to keep. Can add custom keywords. | POST /v1/discovery/keywords/generate (exists) |
| 5. First Scan | Auto-discovers top 5 subreddits and runs first scan. Shows progress: 'Searching r/SaaS... Found 3 matches'. Ends with: 'We found X opportunities! View them now.' | POST /v1/scans (needs async) |
| 6. Dashboard Landing | Dashboard now populated with data. Setup progress shows 100%. Confetti animation. Prompt: 'Your first opportunities are ready! Click any to generate a reply.' | GET /v1/dashboard (exists) |

## 6.2 Core Reply Generation Flow (Improved)

- User sees opportunity card in feed with score badge, title, subreddit, and body preview.

- Clicks 'Draft Reply' button. Loading spinner appears on button. Background: API generates reply.

- Reply appears in a slide-out drawer on the right side. Shows: generated reply in an editable text area, rationale explanation below, 'Regenerate' button, 'Copy to clipboard' button.

- User edits reply if needed. Character count shows limit. Preview mode shows how it will look on Reddit.

- Clicks 'Copy to Clipboard' or 'Send for Approval' (if team workflow enabled). Toast notification confirms action.

- Opportunity status auto-updates to 'Drafting' or 'Posted'. Activity log records the action.

## 6.3 AI Visibility Tracking Flow (New)

- User navigates to AI Visibility screen. If first time, sees guided setup: 'Add prompts that your customers would ask AI.'

- User creates a Prompt Set: names it (e.g., 'Product Recommendations'), adds 5-10 prompts, selects target models.

- Clicks 'Run Now' or schedules daily execution. System queues prompt runs via Celery.

- Results populate within minutes. Dashboard shows: brand mentioned in 6 of 10 prompts on ChatGPT, 3 of 10 on Perplexity.

- Share of voice chart updates. Anomaly detection alerts if visibility drops below threshold.

- Citation panel shows which URLs were referenced. Source gaps highlight where competitors are cited but brand is not.

# 7. UI/UX Redesign Direction

## 7.1 Design Principles

- Clarity First: Every element serves a purpose. Remove decorative clutter. Users should never wonder 'what does this button do?'

- Progressive Disclosure: Show simple by default, reveal complexity on demand. New users see guided flows. Power users access advanced settings.

- Immediate Feedback: Every action produces visible feedback within 200ms. Loading states, success toasts, error explanations, progress indicators.

- Trust Through Transparency: Show users what the system is doing. 'Analyzing 5 subreddits...' instead of a generic spinner. Explain scores. Show sources.

- Consistent Patterns: Same component for same purpose everywhere. One button style for primary actions. One card style for data display. One toast style for feedback.

## 7.2 Key UX Improvements

Empty States

Every page needs a purposeful empty state with three elements: an illustration or icon, a clear heading explaining what will appear here, and a CTA button to take the first action. Example: Opportunities empty state shows a search illustration with 'No opportunities found yet' heading and 'Run Your First Scan' button.

Loading States

Three patterns for different contexts: button loading (spinner replaces text, button stays same size, disabled), page loading (skeleton UI matching the content structure), and background processing (toast notification: 'Scanning Reddit... This may take 30 seconds' with progress bar).

Error States

Four severity levels, each with distinct styling: info (blue, informational), success (green, confirmation), warning (amber, attention needed), error (red, action failed). Each includes: icon, title, description, and suggested action or retry button.

Confirmation Patterns

All destructive actions require confirmation: modal dialog with clear title ('Delete this keyword?'), description of consequences ('This keyword will no longer be used in scans. This action cannot be undone.'), and two buttons: 'Cancel' (secondary) and 'Delete' (red/danger).

# 8. Design System Recommendations

## 8.1 Color System

| Token | Value | Usage |
| --- | --- | --- |
| Primary | #1A1A2E | Navigation, headers, primary text. Dark and authoritative. |
| Accent | #E94560 | CTAs, active states, brand highlight. Energetic and attention-grabbing. |
| Blue | #0F3460 | Links, informational elements, secondary headings. Professional trust. |
| Success | #16A085 | Completed states, positive metrics, confirmation messages. |
| Warning | #E67E22 | Approaching limits, attention needed, partial states. |
| Error | #E74C3C | Failed actions, validation errors, critical alerts. |
| Surface | #F8F9FC | Page background. Slightly cool to avoid sterile white. |
| Card | #FFFFFF | Card backgrounds. Pure white for content separation. |
| Border | #E5E7EB | Dividers, table borders, input outlines. Subtle separation. |
| Muted Text | #6B7280 | Secondary text, timestamps, helper text. Readable but recessive. |

## 8.2 Typography System

| Name | Size | Weight | Line Height | Usage |
| --- | --- | --- | --- | --- |
| Display | 28px | 700 (Bold) | 1.2 | Page titles only |
| Heading 1 | 24px | 700 (Bold) | 1.3 | Section headers |
| Heading 2 | 20px | 600 (Semibold) | 1.3 | Subsection headers |
| Heading 3 | 16px | 600 (Semibold) | 1.4 | Card titles, labels |
| Body | 14px | 400 (Regular) | 1.5 | Default paragraph text |
| Body Small | 13px | 400 (Regular) | 1.5 | Table cells, descriptions |
| Caption | 12px | 400 (Regular) | 1.4 | Timestamps, helper text, meta info |
| Overline | 11px | 600 (Semibold) | 1.4 | Category labels, uppercase tags |

Font stack: Inter, -apple-system, BlinkMacSystemFont, Segoe UI, sans-serif. Inter is the modern SaaS standard: clean, readable, free, and excellent at small sizes.

## 8.3 Spacing System

Consolidate the current 16 different gap values down to 8 using a 4px base grid:

| Token | Value | Usage |
| --- | --- | --- |
| xs | 4px | Tight inline spacing, icon-to-text gap |
| sm | 8px | Between related elements within a group |
| md | 12px | Between form fields, list items |
| lg | 16px | Between groups within a card |
| xl | 24px | Between cards, between sections |
| 2xl | 32px | Between major sections |
| 3xl | 48px | Page-level vertical spacing |
| 4xl | 64px | Between page regions |

## 8.4 Component Specifications

Buttons

| Variant | Style | When to Use |
| --- | --- | --- |
| Primary | Accent bg (#E94560), white text, 8px 16px padding, 6px radius | Main CTA per section (Save, Generate, Run Scan) |
| Secondary | White bg, accent border, accent text | Secondary actions (Cancel, Edit, View All) |
| Ghost | Transparent bg, muted text, no border | Tertiary actions (Copy, Dismiss, Skip) |
| Danger | Error red bg, white text | Destructive actions (Delete, Remove, Revoke) |
| Disabled | Gray bg, muted text, cursor not-allowed, 50% opacity | When action is unavailable |
| Loading | Same style + spinner icon replacing text. Same width to prevent layout shift | While processing |

Cards

All cards: white background, 1px border (#E5E7EB), 8px border-radius, 24px padding, subtle shadow (0 1px 3px rgba(0,0,0,0.08)). Hover state: shadow increases to (0 4px 12px rgba(0,0,0,0.1)).

Form Inputs

All inputs: 40px height, 12px 16px padding, 6px radius, 1px border (#D1D5DB). Focus state: accent border + subtle accent shadow ring. Error state: red border + red shadow ring + error text below. Proper HTML label elements associated via htmlFor attribute.

Toast Notifications

Position: bottom-right, stacking upward. Auto-dismiss: 5s for success, 8s for error, persistent for warnings. Structure: icon (left), title + description (center), close button (right). Width: 360px max. Animation: slide in from right, fade out.

# 9. Backend / Data / API Requirements

## 9.1 New API Endpoints Required

| Module | Endpoint | Purpose |
| --- | --- | --- |
| Visibility | POST /v1/prompt-sets | Create a prompt set with grouped prompts |
| Visibility | GET /v1/prompt-sets | List prompt sets for project |
| Visibility | POST /v1/prompt-sets/{id}/run | Trigger prompt execution across models |
| Visibility | GET /v1/visibility/summary | Aggregated share of voice, mentions, citations |
| Visibility | GET /v1/visibility/trends | Time-series visibility data for charts |
| Visibility | GET /v1/visibility/competitors | Competitor share of voice rankings |
| Sources | GET /v1/citations | Paginated citation list with filters |
| Sources | GET /v1/sources/domains | Domain-level citation leaderboard |
| Sources | GET /v1/sources/gaps | Source gaps where competitors beat brand |
| Notifications | GET /v1/notifications | Paginated notification list |
| Notifications | PUT /v1/notifications/{id}/read | Mark notification as read |
| Notifications | POST /v1/notifications/read-all | Mark all as read |
| Auth | POST /v1/auth/forgot-password | Send password reset email |
| Auth | POST /v1/auth/reset-password | Reset password with token |
| Auth | POST /v1/auth/refresh | Refresh JWT token |
| Usage | GET /v1/usage | Current plan usage metrics |
| Health | GET /health | System health check (DB, Redis, APIs) |
| Activity | GET /v1/activity | Recent activity timeline for workspace |

## 9.2 Backend Architecture Fixes Required

Immediate Fixes (Week 1)

- Add Python logging with JSON formatter to every module. Configure log levels per environment.

- Integrate Sentry for exception tracking. Add breadcrumbs for API calls.

- Add request correlation ID middleware. Generate UUID per request, pass to all log messages.

- Add SlowAPI rate limiting: 60 req/min per user general, 5 req/min for scan/generate endpoints.

- Fix CORS: whitelist specific methods (GET, POST, PUT, DELETE), specific headers (Authorization, Content-Type).

- Add URL validation to website analysis: https-only, no private IPs, 5-second timeout.

Week 2-3 Fixes

- Move _run_scan() to Celery task. Return scan_id immediately. Add GET /v1/scans/{id}/status polling endpoint.

- Replace bare 'except Exception: continue' with specific exception handling and logging.

- Add pagination to all list endpoints: default limit=20, max limit=100.

- Implement token blacklist in Redis. Add refresh token flow.

- Set up Alembic for database migrations. Create initial migration from current models.

- Build email service using SMTP config. Send invitation emails, password reset, welcome email.

- Add soft delete (is_deleted, deleted_at) to Project, Persona, DiscoveryKeyword, MonitoredSubreddit.

- Fix N+1 queries in dashboard using SQLAlchemy selectinload().

## 9.3 AI Model Runner Architecture

The model runner is the most critical new backend service. It must execute prompts across multiple AI models reliably.

Architecture

- Task Queue: Celery task per prompt-model pair. Allows parallel execution across models.

- Model Adapters: Abstract base class with implementations for each model: OpenAIAdapter (ChatGPT), PerplexityAdapter, GeminiAdapter, ClaudeAdapter. Each handles auth, rate limits, and response parsing.

- Response Parser: Extract brand mentions, competitor mentions, cited URLs, sentiment. Store raw response and parsed metadata.

- Retry Policy: Exponential backoff with jitter. Max 3 retries. Dead letter queue for persistent failures.

- Scheduling: Celery Beat for daily/weekly prompt runs. Configurable per prompt set.

# 10. Admin, Settings & Billing Requirements

## 10.1 Billing System Improvements

Current Problems

- No upgrade/downgrade buttons in UI

- No invoice history or payment method management

- Usage metrics tracked at call time with race conditions

- Redemption codes have no expiration

- No visual usage meters showing plan consumption

Required Changes

- Add UsageMetric model with atomic increment/decrement. Track: projects_used, keywords_used, subreddits_used, scans_this_month, drafts_this_month.

- Build billing dashboard with visual meters: '23 of 50 keywords used' with progress bar.

- Add upgrade prompt when user hits 80% of any limit. Show comparison of current plan vs next tier.

- Implement Stripe Customer Portal for payment method, invoices, and plan changes.

- Add expires_at to Redemption model. Validate expiry on redemption.

## 10.2 Revised Pricing Strategy

Current pricing ($0 / $79 / $199) should be restructured to reflect the new AI Visibility capabilities:

| Plan | Price | Key Inclusions |
| --- | --- | --- |
| Free | $0/mo | 1 project, 10 keywords, 5 subreddits, 3 prompt sets, 50 prompt runs/mo, Reddit only, Basic dashboard |
| Starter | $99/mo | 3 projects, 50 keywords, 25 subreddits, 10 prompt sets, 500 prompt runs/mo, Reddit + Quora, Share of voice dashboard, Email alerts |
| Growth | $249/mo | 10 projects, 150 keywords, 75 subreddits, 25 prompt sets, 2000 prompt runs/mo, All platforms, Source intelligence, Competitor tracking, Team collaboration (5 seats) |
| Enterprise | Custom | Unlimited projects, Custom limits, All platforms, Experiment framework, CRM integration, Revenue attribution, Dedicated support, SLA guarantee |

## 10.3 Team Management Requirements

- Invite members via email with role selection (Admin, Member, Viewer)

- Viewer role: read-only access to dashboards and reports

- Member role: can create content, run scans, generate drafts

- Admin role: all Member permissions plus settings, billing, and team management

- Owner role: all Admin permissions plus workspace deletion and ownership transfer

- Activity feed showing who did what: 'Sarah generated a reply for r/startups thread'

# 11. Growth, Positioning & Conversion Improvements

## 11.1 Positioning Statement

Current: 'Find Reddit threads where your expertise fits, and draft helpful answers.' This is too narrow and undersells the platform.

Recommended: 'Measure, influence, and prove your brand's AI recommendation share, safely.' This positions the product as a comprehensive AI visibility platform, not just a Reddit reply tool.

## 11.2 Landing Page Improvements

- Hero Section: Headline: 'Know When AI Recommends You. And When It Doesn't.' Subheadline: 'Track your brand across ChatGPT, Perplexity, Gemini, and Claude. Discover which sources AI cites. Place your brand where it matters.' Primary CTA: 'Start Free' (green button). Secondary: 'Watch 2-min demo'

- Social Proof Bar: Logo row: 'Trusted by 200+ brands' with recognizable logos. Below: 3 stat boxes showing '10M+ AI responses tracked', '50K+ opportunities found', '3x average visibility improvement'

- Feature Sections: Three sections with screenshots: (1) AI Visibility Dashboard showing share of voice chart, (2) Source Intelligence showing citation gaps, (3) Community Engagement showing opportunity scoring and AI reply drafting

- Trust Section: Security badges, data handling policy, SOC2 mention (even if 'in progress'), 'Your data is never shared with AI models' assurance

- Pricing Section: Side-by-side plan comparison with feature checkmarks. Highlight Growth plan as 'Most Popular'. Annual discount toggle.

- FAQ Section: 8-10 common questions: 'How often does it check AI responses?', 'Which AI models do you track?', 'Is this against Reddit's terms of service?', etc.

## 11.3 Retention Loops

- Weekly Visibility Digest: Email every Monday: 'Your brand was mentioned in 23 AI responses this week (+5 from last week). 3 new source gaps found. Top opportunity: r/SaaS thread with 87/100 match score.'

- Visibility Drop Alerts: Real-time alert when share of voice drops below threshold. 'Your ChatGPT visibility dropped 15% this week. A competitor was cited 8 more times. View affected prompts.'

- Monthly ROI Report: Auto-generated report: prompts tracked, visibility changes, opportunities found, drafts generated, estimated brand exposure increase.

- Usage-Based Upgrade Nudges: When user hits 80% of plan limit: 'You have used 45 of 50 keywords. Upgrade to Growth for 150 keywords and Source Intelligence.'

# 12. Phase-Wise Build Roadmap

## Phase 0: Foundation Fixes (Weeks 1-2)

These are non-negotiable fixes before building any new features. Without them, the product is unstable.

| Task | Area | Est. |
| --- | --- | --- |
| Structured logging + Sentry integration | Backend | 2 days |
| Move scan operations to Celery async tasks | Backend | 3 days |
| Rate limiting middleware | Backend | 1 day |
| Fix CORS, add SSRF protection | Backend | 1 day |
| Password reset flow (backend + frontend) | Full Stack | 2 days |
| Toast notification system (replace .notice divs) | Frontend | 2 days |
| Loading states on all buttons and async operations | Frontend | 2 days |
| Client-side form validation | Frontend | 2 days |
| Confirmation dialogs for all destructive actions | Frontend | 1 day |
| Pagination on all list endpoints | Backend | 2 days |

## Phase 1: CrowdReply Parity (Weeks 3-10)

Build the core AI Visibility product that matches CrowdReply's primary value proposition.

| Task | Area | Est. |
| --- | --- | --- |
| Prompt Library model + management API + UI | Full Stack | 5 days |
| AI Model Runner Service (ChatGPT + Perplexity adapters) | Backend | 7 days |
| Gemini + Claude model adapters | Backend | 4 days |
| Brand mention + competitor detection engine | Backend | 4 days |
| Citation URL extraction and storage | Backend | 3 days |
| Share of voice calculation + storage | Backend | 3 days |
| AI Visibility dashboard (trends, KPIs, competitor chart) | Frontend | 7 days |
| Source Intelligence: citation list + domain leaderboard | Full Stack | 5 days |
| Source gap analysis view | Full Stack | 3 days |
| Quora monitoring integration | Backend | 5 days |
| Redesigned Opportunities page with filters and drawer | Frontend | 5 days |
| Email service: invitations, password reset, alerts | Backend | 3 days |
| Notification center (in-app) | Full Stack | 3 days |
| Redesigned Dashboard with KPIs, trends, activity feed | Frontend | 4 days |
| Guided onboarding wizard for new users | Frontend | 3 days |

## Phase 2: Clearly Better (Weeks 11-20)

| Task | Area | Est. |
| --- | --- | --- |
| Google AI Overviews + Copilot tracking | Backend | 7 days |
| Facebook group monitoring | Backend | 5 days |
| Domain influence graph visualization | Frontend | 5 days |
| Prompt clustering and AI response framing analysis | Backend | 5 days |
| Content Studio: drafts, approval queue, posting history | Full Stack | 7 days |
| Compliance/policy scoring engine | Backend | 5 days |
| Auto-posting to Reddit and Quora (with safety checks) | Backend | 7 days |
| Experiment framework: campaigns, A/B tests, outcomes | Full Stack | 10 days |
| CRM/GA4 connector architecture | Backend | 5 days |
| Executive reporting with PDF export | Full Stack | 5 days |
| Design system implementation (shared component library) | Frontend | 7 days |
| Settings restructure: team, billing, integrations tabs | Full Stack | 5 days |
| Usage meters and upgrade prompts | Frontend | 3 days |
| Weekly visibility digest email | Backend | 3 days |

## Phase 3: Category Leader (Weeks 21+)

| Task | Area | Est. |
| --- | --- | --- |
| Revenue attribution engine | Full Stack | 15 days |
| Causal attribution (action to visibility change) | Backend | 15 days |
| Creator/expert marketplace | Full Stack | 20 days |
| Region/persona simulation for AI responses | Backend | 10 days |
| Predictive citation probability ML model | Backend | 15 days |
| Budget allocator across channels and models | Full Stack | 7 days |
| Category benchmark datasets | Backend | 10 days |
| Enterprise SSO (SAML/OIDC) | Backend | 7 days |
| Audit log viewer with search and export | Full Stack | 5 days |
| API developer portal with documentation | Full Stack | 7 days |

# 13. Quick Wins to Implement Immediately

These can each be done in under 1 day and will immediately improve the product quality.

| # | Quick Win | Why It Matters | Estimate |
| --- | --- | --- | --- |
| 1 | Add loading spinners to all buttons with async operations | Prevents double-clicks, shows system is working | 2-3 hours |
| 2 | Create 4 distinct .notice variants: info (blue), success (green), warning (amber), error (red) | Users can distinguish feedback types | 1-2 hours |
| 3 | Add 'Are you sure?' confirmation modal before all delete actions | Prevents accidental data loss | 2-3 hours |
| 4 | Add character count indicators to all textareas | Helps users write appropriate-length content | 1 hour |
| 5 | Fix persona form to include pain_points, goals, triggers, preferred_subreddits fields | Currently only captures 3 of 7 model fields | 2-3 hours |
| 6 | Add edit functionality to existing personas, keywords, and subreddits | Currently read-only after creation | 3-4 hours |
| 7 | Add 'Copy to clipboard' button on generated reply drafts | Critical missing feature for the core workflow | 30 min |
| 8 | Add a proper 404 page | Currently shows broken/blank page on invalid routes | 30 min |
| 9 | Add 'Forgot password?' link on login page (UI only, backend in Phase 0) | Reduces user frustration even before backend is ready | 15 min |
| 10 | Fix Discovery page to show clear Step 1, 2, 3 indicators | Current grid layout confuses workflow order | 2-3 hours |
| 11 | Add 'View all opportunities' link on dashboard | Dashboard shows 6 but users don't know more exist | 15 min |
| 12 | Add score explanations via tooltips on opportunity cards | Users don't understand what 87/100 means | 1-2 hours |

# 14. Final 'Ideal Version' Blueprint

This is what the fully-realized RedditFlow platform looks like after all phases are complete.

## 14.1 Product Identity

- Name: RedditFlow (consider renaming to something broader like 'BrandSignal' or 'CiteTrack' since it is no longer Reddit-only)

- Tagline: Measure, influence, and prove your AI recommendation share.

- Category: AI Visibility and Community Engagement Platform

- Target Customer: B2B SaaS companies, DTC brands, agencies managing brand reputation in AI-influenced discovery

## 14.2 Complete Module Map

| Module | Complete Feature Set |
| --- | --- |
| Visibility Intelligence | Prompt library, multi-model runners (6 AI surfaces), brand mention detection, share of voice, trend analysis, anomaly detection, competitor tracking, historical benchmarks |
| Source Intelligence | Citation extraction, domain influence graph, URL-level scoring, source gap analysis, content format classification, freshness weighting, influence score trends |
| Social Listening | Reddit + Quora + Facebook monitoring, multi-factor opportunity scoring (0-100), help-seeking intent detection, early thread detection, cross-platform unified feed, real-time alerts |
| Safe Activation | AI reply drafting, original post drafting, compliance/policy scoring, approval workflows, auto-posting with safety checks, employee advocacy, creator marketplace |
| Experimentation | Campaign setup, A/B testing framework, intervention logging, pre/post measurement, controlled prompt cohort testing, statistical significance calculation |
| Attribution | CRM connectors (HubSpot, Salesforce, GA4), revenue attribution engine, funnel tracking, branded search lift measurement, executive ROI reports |
| Platform | Multi-tenant workspaces, RBAC with 4 roles, JWT with refresh tokens, Stripe billing with 4 tiers, notification center, audit trail, email system, webhook system, API developer portal |

## 14.3 Technical Architecture

Backend Stack

- FastAPI (Python) with async endpoints

- PostgreSQL for application state

- TimescaleDB or ClickHouse for time-series visibility data

- Redis for caching, rate limiting, token blacklist, Celery broker

- Celery workers for async operations (scans, model runs, email, webhooks)

- Celery Beat for scheduled prompt execution

- Sentry for error tracking

- Structured JSON logging to stdout (ELK/Datadog compatible)

- Alembic for database migrations

Frontend Stack

- Next.js 16+ with App Router

- TypeScript with strict mode

- Tailwind CSS with custom design tokens

- Shared component library (Button, Input, Card, Toast, Modal, Table, EmptyState, Skeleton)

- React Query for server state management

- Recharts for data visualization

- React Hook Form + Zod for form validation

Infrastructure

- Docker Compose for local development

- Kubernetes manifests for production

- GitHub Actions for CI/CD

- Health check endpoints for all external dependencies

- Automated database backups

## 14.4 Folder / Module Structure (Recommended)

Restructure the backend from the current flat layout to a modular domain-driven structure:

| Path | Files | Responsibility |
| --- | --- | --- |
| app/modules/auth/ | routes.py, service.py, models.py, schemas.py | Authentication, password reset, token management |
| app/modules/workspace/ | routes.py, service.py, models.py | Workspace CRUD, team management, invitations |
| app/modules/brand/ | routes.py, service.py, models.py | Brand profile, website analysis, voice settings |
| app/modules/audience/ | routes.py, service.py, models.py | Personas, keywords, monitored communities |
| app/modules/visibility/ | routes.py, service.py, models.py, runners/ | Prompt sets, model runners, mention detection, share of voice |
| app/modules/sources/ | routes.py, service.py, models.py | Citations, domains, influence scores, gaps |
| app/modules/opportunities/ | routes.py, service.py, models.py, scoring.py | Social listening, scanning, opportunity scoring |
| app/modules/content/ | routes.py, service.py, models.py | Drafts, templates, approval queue, posting |
| app/modules/experiments/ | routes.py, service.py, models.py | Campaigns, A/B tests, outcomes |
| app/modules/billing/ | routes.py, service.py, models.py | Plans, subscriptions, usage, Stripe integration |
| app/modules/notifications/ | routes.py, service.py, models.py | In-app notifications, email digests, alerts |
| app/core/ | config.py, security.py, middleware.py, logging.py | Shared infrastructure |
| app/services/ | email.py, redis.py, celery_app.py | Shared services |

## 14.5 What Makes This Better Than CrowdReply

This blueprint produces a platform that is superior across every dimension:

| Dimension | CrowdReply | Your Platform |
| --- | --- | --- |
| Multi-Surface Intelligence | CrowdReply tracks ChatGPT, Perplexity, Gemini, Claude | You also track Google AI Overviews, Copilot, and category-specific answer boxes |
| Source Graph Intelligence | CrowdReply lists citations | You build a full domain influence graph with URL-level scoring, gap analysis, and content format classification |
| Compliance-First Engagement | CrowdReply uses managed anonymous accounts (ToS risk) | You prioritize employee advocacy, founder identity, compliance scoring, and policy checks before posting |
| Experimentation Framework | CrowdReply: no testing capability | You offer campaign setup, A/B testing, pre/post measurement, and statistical significance |
| Revenue Attribution | CrowdReply: no attribution | You connect AI visibility to CRM pipeline, demo requests, branded search lift, and conversions |
| Opportunity Scoring | CrowdReply: basic thread discovery | You have a multi-factor 0-100 scoring algorithm with keyword matching, intent detection, freshness, competition, and audience overlap |
| Brand Intelligence | CrowdReply: manual brand setup | You auto-analyze websites, generate personas, and suggest keywords from brand profile |
| Enterprise Readiness | CrowdReply: credit-based, single-user oriented | You have RBAC, team collaboration, audit logs, approval workflows, webhook integrations, and encrypted secrets |

This is the blueprint for a platform that does not just match CrowdReply but fundamentally surpasses it by combining AI visibility tracking with source intelligence, compliance-safe engagement, causal experimentation, and revenue attribution. Build it phase by phase, starting with foundation fixes, then CrowdReply parity, then the differentiators that make you the category leader.