## Executive Summary
RedditFlow vs CrowdReply — Gap Analysis
What you have, what's missing, and what to build for V1 / V2 / V3
Category | Built | Partial | Missing | Total Features | Completion %
A. Prompt / AI Visibility Tracking | 0 | 0 | 8 | 8 | 0%
B. Citation & Source Intelligence | 0 | 1 | 5 | 6 | 0%
C. Social Listening & Thread Discovery | 5 | 2 | 3 | 10 | 50%
D. Engagement / Activation Engine | 3 | 2 | 5 | 10 | 30%
E. Experimentation & Attribution | 0 | 0 | 7 | 7 | 0%
F. Platform & SaaS Infrastructure | 12 | 2 | 3 | 17 | 70.59%
G. Reporting & Dashboards | 1 | 1 | 4 | 6 | 16.67%
TOTAL | 21 | 8 | 35 | 64 | 32.81%

## Detailed Gap Analysis
Category | Feature | CrowdReply Has It? | Your App Status | What You Have Now | What's Missing / To Build | Priority (V1/V2/V3) | Effort Estimate | Notes
A. Prompt Tracking | Define prompts per brand/category | Yes | Missing | Not built | Full prompt library: create, cluster, tag prompts by intent/persona/funnel stage | V1 | Medium | Core CrowdReply feature
A. Prompt Tracking | Run prompts across AI models (ChatGPT, Perplexity, Gemini, Claude) | Yes | Missing | Not built | AI model runner service: schedule prompt execution across 4+ models, store responses | V1 | High | Need API access to each model or web scraping
A. Prompt Tracking | Daily/scheduled prompt execution | Yes | Missing | Not built | Celery-based scheduler for periodic prompt runs (daily/weekly) | V1 | Medium | You already have Celery infra
A. Prompt Tracking | Brand mention detection in AI responses | Yes | Missing | Not built | NLP/regex brand + competitor mention extraction from AI responses | V1 | Medium
A. Prompt Tracking | Competitor tracking in AI responses | Yes | Missing | Not built | Track which competitors appear alongside or instead of brand | V1 | Medium
A. Prompt Tracking | Share of voice / recommendation rate | Yes | Missing | Not built | Calculate % of prompts where brand is mentioned vs competitors | V2 | Medium
A. Prompt Tracking | Historical trend lines & anomaly detection | Yes | Missing | Not built | Time-series storage + trend visualization + alerting on drops | V2 | High | Need ClickHouse or similar
A. Prompt Tracking | Multi-model comparison dashboard | Yes | Missing | Not built | Side-by-side view: how brand appears across different AI models | V2 | Medium
B. Citation Intelligence | Citation/URL extraction from AI responses | Yes | Missing | Not built | Parse AI responses to extract cited URLs, domains, sources | V1 | Medium | Core differentiator
B. Citation Intelligence | Source gap analysis vs competitors | Yes | Missing | Not built | Show where competitors are cited but brand is not | V1 | Medium
B. Citation Intelligence | Domain-level citation graph | Yes | Missing | Not built | Graph DB or relation table: which domains are cited for which prompts | V2 | High | CrowdReply's core IP
B. Citation Intelligence | URL-level influence scoring | Yes | Missing | Not built | Score URLs by citation frequency, recency, model coverage | V2 | High
B. Citation Intelligence | Content format analysis (what types get cited) | Yes | Missing | Not built | Classify cited content: review, comparison, discussion, tutorial, etc. | V2 | Medium
B. Citation Intelligence | Source freshness/authority/repetition weighting | Yes | Partial | Subreddit fit scoring exists but not for citations | Extend scoring to citation sources with freshness, authority, repetition weights | V2 | Medium | You have scoring infra in scoring.py
C. Social Listening | Reddit keyword search & monitoring | Yes | Built | ScanRun + Opportunity discovery across subreddits | Already built | - | - | Core feature working
C. Social Listening | Subreddit discovery & analysis | Yes | Built | MonitoredSubreddit + SubredditAnalysis with AI | Already built | - | -
C. Social Listening | Multi-factor opportunity scoring | Yes | Built | OpportunityScore with keyword, intent, freshness, competition scoring | Already built | - | - | Your scoring is solid
C. Social Listening | Real-time alerts (email/Slack) | Yes | Partial | Webhook endpoints exist but no Slack/email integration built | Build Slack bot + email digest for new high-score opportunities | V1 | Medium | Webhook infra is there
C. Social Listening | Variable listening frequency by plan | Yes | Partial | Plan entitlements exist but no frequency control | Add scan frequency limits per plan tier | V1 | Low
C. Social Listening | Quora monitoring | Yes | Missing | Not built — Reddit only | Add Quora API/scraping + opportunity scoring for Quora | V1 | High | CrowdReply covers Quora
C. Social Listening | Facebook group monitoring | Yes | Missing | Not built | Add Facebook Graph API integration for group monitoring | V2 | High | CrowdReply covers Facebook
C. Social Listening | Early thread detection (before AI cites) | Yes | Built | 72-hour window scanning with freshness scoring | Tighten to real-time or near-real-time for trending threads | V2 | Medium
C. Social Listening | Help-seeking intent detection | Yes | Built | Intent phrase matching in scoring.py | Already built | - | -
C. Social Listening | Cross-platform unified feed | Yes | Missing | Reddit-only feed | Unified opportunity feed across Reddit, Quora, Facebook | V2 | Medium | After adding platforms
D. Engagement | AI reply draft generation | Yes | Built | ReplyDraft with customizable PromptTemplates | Already built and customizable | - | - | Strong feature
D. Engagement | AI original post draft generation | Yes | Built | PostDraft generation with brand voice | Already built | - | -
D. Engagement | Customizable prompt templates | Yes | Built | PromptTemplate model with system instructions | Already built | - | -
D. Engagement | Engagement credits / task-based execution | Yes | Partial | Plan entitlements exist but no credit system | Build credit/token system: deduct on draft generation or posting | V1 | Medium | CrowdReply's monetization model
D. Engagement | Managed community profiles (aged Reddit accounts) | Yes | Missing | Not built | Account pool management for posting (HIGH RISK — platform ToS) | V3 | Very High | Legally risky; consider compliance-first approach
D. Engagement | Auto-posting to Reddit/Quora | Yes | Missing | Manual workflow only — 'drafting' status | Reddit API posting, Quora posting (or browser automation) | V2 | High | Currently draft-only
D. Engagement | Compliance/policy scoring before posting | No | Missing | Not built | Check subreddit rules, platform ToS, spam risk before posting | V2 | Medium | YOUR ADVANTAGE over CrowdReply
D. Engagement | Employee advocacy / founder identity posting | No | Missing | Not built | Verified brand rep posting workflow with disclosure | V2 | Medium | Safer than anonymous accounts
D. Engagement | Draft approval workflow | Yes | Partial | Status transitions exist (NEW > SAVED > DRAFTING > POSTED) | Add multi-user approval chain, reviewer roles, comments on drafts | V2 | Medium
D. Engagement | Creator/expert marketplace | No | Missing | Not built | Marketplace connecting brands with genuine community contributors | V3 | Very High | V3 differentiator
E. Experimentation | Campaign / experiment setup | No | Missing | Not built | Campaign model: group actions, define hypothesis, set timeframe | V2 | High | Big differentiator
E. Experimentation | Pre/post intervention measurement | No | Missing | Not built | Track AI visibility before and after engagement actions | V2 | High
E. Experimentation | Controlled prompt cohort testing | No | Missing | Not built | A/B test: control vs intervention prompts, measure delta | V2 | High
E. Experimentation | Causal attribution (action → visibility change) | No | Missing | Not built | Statistical model linking specific actions to specific visibility changes | V3 | Very High | Category's missing layer
E. Experimentation | CRM / GA4 / HubSpot / Salesforce connectors | No | Missing | Not built | Integration APIs to pull pipeline, demo, conversion data | V2 | High
E. Experimentation | Revenue attribution (visibility → pipeline) | No | Missing | Not built | Tie AI mention changes to branded search lift, demo requests, conversions | V3 | Very High
E. Experimentation | Executive reporting / shareable reports | Yes | Missing | Not built | PDF/dashboard export, scheduled email reports, shareable links | V2 | Medium
F. SaaS Platform | User authentication (JWT) | Yes | Built | JWT auth with scrypt hashing | Already built | - | -
F. SaaS Platform | Multi-tenant workspaces | Yes | Built | Workspace model with memberships | Already built | - | -
F. SaaS Platform | Role-based access (Owner/Admin/Member) | Yes | Built | RBAC with 3 roles | Already built | - | -
F. SaaS Platform | Team invitations | Yes | Built | Token-based email invitations | Already built | - | -
F. SaaS Platform | Tiered billing / Stripe | Yes | Built | 3 plans: Free/$79/$199 with Stripe | Already built | - | -
F. SaaS Platform | Plan entitlements enforcement | Yes | Built | Per-workspace feature limits | Already built | - | -
F. SaaS Platform | Webhook system | Yes | Built | WebhookEndpoint with signing, test delivery | Already built | - | -
F. SaaS Platform | Encrypted secrets storage | Yes | Built | Fernet AES encryption for integration creds | Already built | - | -
F. SaaS Platform | Audit logging | Yes | Built | AuditEvent model with full trail | Already built | - | -
F. SaaS Platform | Async task processing (Celery) | Yes | Built | Celery + Redis workers | Already built | - | -
F. SaaS Platform | Brand/project management | Yes | Built | Project + BrandProfile models | Already built | - | -
F. SaaS Platform | Website analysis / brand intelligence | Yes | Built | ProductCopilot scrapes and analyzes brand sites | Already built | - | -
F. SaaS Platform | Collaboration features (approvals, audit logs) | Yes | Partial | Audit logs exist, no approval chains | Add draft approval workflows, activity feeds, @mentions | V2 | Medium
F. SaaS Platform | API for integrations | Yes | Partial | V1 REST API exists but limited | Expand API: public developer docs, API keys, rate limits, OAuth | V2 | Medium
F. SaaS Platform | Promotional codes / redemptions | Yes | Built | Redemption model with promo codes | Already built | - | - | Unique to your platform
F. SaaS Platform | Google AI Overviews / AI Mode tracking | No (CrowdReply) | Missing | Not built | Add Google SERP + AI Overview scraping/API | V2 | High | Competitors like Otterly have this
F. SaaS Platform | Copilot (Microsoft) tracking | No | Missing | Not built | Add Copilot monitoring | V2 | High
G. Reporting | Dashboard with KPI cards | Yes | Built | Setup checklist + KPI cards + top opportunities | Already built | - | -
G. Reporting | Share of voice dashboard | Yes | Missing | Not built | Visual: brand vs competitors across AI models over time | V1 | Medium | Depends on prompt tracking
G. Reporting | Citation source dashboard | Yes | Missing | Not built | Visual: top cited domains, gaps, influence graph | V2 | Medium
G. Reporting | Campaign performance reports | Yes | Missing | Not built | Pre/post metrics, ROI, engagement outcomes per campaign | V2 | Medium
G. Reporting | Scheduled email reports | Yes | Missing | Not built | Weekly/monthly digest emails with key metrics | V2 | Low
G. Reporting | Competitor comparison view | Yes | Partial | Brand competitor info in project, but no comparison dashboard | Side-by-side competitor visibility comparison | V1 | Medium

## Roadmap V1-V2-V3
V1 — CrowdReply Parity (Target: 8-12 weeks)
Feature | Description | Effort | Timeline
Prompt library & management UI | Define prompts by intent, persona, funnel stage | Medium | Week 1-2
AI model runner (ChatGPT, Perplexity, Gemini, Claude) | API integration to run prompts, store responses | High | Week 2-4
Brand mention detection in AI responses | NLP extraction of brand + competitor mentions | Medium | Week 3-4
Citation URL extraction | Parse AI responses to extract cited sources | Medium | Week 3-4
Source gap analysis | Show where competitors cited but brand isn't | Medium | Week 5-6
Quora monitoring | Add Quora as second platform for listening | High | Week 5-7
Slack/email alerts for opportunities | Real-time notifications on high-score threads | Medium | Week 6-7
Engagement credit system | Credit/token economics for draft generation | Medium | Week 7-8
Share of voice dashboard | Brand vs competitors across AI models | Medium | Week 8-9
Competitor comparison view | Side-by-side visibility comparison | Medium | Week 9-10
Basic AI visibility reporting | Export-ready visibility metrics | Medium | Week 10-11
Scan frequency by plan tier | Variable listening frequency per subscription | Low | Week 11-12
V2 — Clearly Better Than CrowdReply (Target: 12-20 weeks after V1)
Feature | Description | Effort | Timeline
Google AI Overviews + Copilot tracking | Expand AI surface coverage beyond ChatGPT/Perplexity | High | Week 1-4
Citation influence graph | Domain and URL-level citation mapping | High | Week 2-5
Facebook group monitoring | Third platform for social listening | High | Week 3-5
AI response framing/sentiment analysis | How positively/negatively brand is framed in AI answers | Medium | Week 4-6
Prompt clustering by intent | Auto-group related prompts, discover patterns | Medium | Week 5-7
Compliance/policy scoring | Pre-post check against subreddit rules, platform ToS | Medium | Week 6-8
Auto-posting to Reddit/Quora | Go from draft-only to optional auto-posting | High | Week 7-9
Employee advocacy workflows | Verified brand rep posting with disclosure | Medium | Week 8-10
Experiment framework | Campaign setup, intervention logging, cohort analysis | High | Week 9-12
CRM/GA4/HubSpot connectors | Pull pipeline and conversion data | High | Week 10-13
Draft approval workflow | Multi-user approval chain with reviewer roles | Medium | Week 12-14
Scheduled email reports + PDF export | Weekly digest, executive PDF reports | Medium | Week 14-16
Content format recommendations | AI suggests what content types get cited most | Medium | Week 16-18
Cross-platform unified feed | Single view for Reddit + Quora + Facebook opportunities | Medium | Week 18-20
V3 — Category Leader (Target: 20+ weeks after V2)
Feature | Description | Effort | Timeline
Causal attribution engine | Statistically link actions to visibility changes | Very High | Ongoing
Revenue attribution | Tie AI visibility to pipeline, demos, conversions | Very High | Ongoing
Creator/expert marketplace | Connect brands with genuine community contributors | Very High | 12+ weeks
Managed account network (policy-safe) | Disclosed, compliance-scored community accounts | Very High | 12+ weeks
Region/persona simulation | Test how AI answers vary by geography and user type | High | 8-10 weeks
Predictive citation probability | ML model: predict which content will get cited | Very High | Ongoing
Budget allocator across channels/models | Optimize spend across platforms and AI surfaces | High | 8-10 weeks
Category benchmark datasets | Industry-level visibility benchmarks | High | Ongoing

## Your Advantages
What You Already Have That CrowdReply Doesn't (or Does Differently)
Your Advantage | Why It Matters | How to Leverage
Sophisticated opportunity scoring (0-100) | CrowdReply appears to do basic thread discovery; your multi-factor scoring with keyword hits, intent, freshness, competition, fit, and audience overlap is more granular | Market this as 'AI-powered opportunity scoring' — it's a real differentiator
AI-powered subreddit analysis | You auto-analyze top post types, audience signals, and posting risks per subreddit | Use this data to feed into compliance scoring and content recommendations
Brand website intelligence (ProductCopilot) | Auto-populates brand profile from URL analysis — CrowdReply likely requires manual setup | One-click onboarding: paste URL, get full brand setup
AI persona generation | Auto-generate customer personas from brand profile — informs keyword and subreddit discovery | This feeds your entire funnel; CrowdReply doesn't appear to have this
Customizable prompt templates | Users can modify AI drafting instructions — more flexible than fixed templates | Expand to community-shared template marketplace
Full webhook system with test delivery | CrowdReply doesn't appear to have developer-grade integration hooks | Position for enterprise: integrate with any internal tool
Encrypted secrets management | Enterprise-grade credential storage for integrations | Important for compliance-conscious customers
Promotional code system | Built-in growth hacking tool for acquisition | Use for partnerships, influencer deals, enterprise pilots
Audit trail | Full event logging — important for enterprise compliance | Highlight in enterprise sales as SOC2-ready foundation
Multi-tenant with RBAC | Team-ready architecture from day one | CrowdReply appears more single-user oriented